UPDRS Predictor

Parkinson's Disease Severity Assessment Tool

Project Initiation Document — Version 2

Multi-class Classification: Mild / Moderate / Severe

| Module | Discipline-Specific AI Project |
| --- | --- |
| Institution | University of Bradford |
| Level | FHEQ Level 5 (Year 2, BSc Applied AI) |
| Client | Dr Ramzi Jaber, University of Bradford |
| Module Sponsor | Prof. Kulvinder Panesar, University of Bradford |
| Document Version | V2.0 — Updated for Multi-class Severity Classification |
| Previous Version | PID V1.0 — Binary Classification (Healthy vs Parkinson's) |
| Date | March 2026 |
| Status | Final |

Group Members:  Ebuka  |  Ryan  |  Avyandra  |  Elvis

# How to Read This Document

This PID covers Version 2 of the UPDRS Predictor. It is structured as a delta document — only sections that changed between V1 and V2 are written in full. Sections that remain the same reference the V1 PID to avoid duplication.

Section markers:

UNCHANGED FROM V1 — this section is identical to V1. Refer to PID V1.

UPDATED FOR V2 — this section has changed and is written in full below.

# Supporting Documents

The following documents support and evidence this V2 PID. They are included in the /docs folder of the project repository.

| Document | Description | Status |
| --- | --- | --- |
| Project Charter V2 | Updated scope, goal, success criteria, team, and risk register for the multi-class severity classification system | Complete — see Project_Charter_V2.docx |
| Quality Assurance Plan V2 | Updated working procedures, V2-specific quality checkpoints, revised evaluation strategy, and deliverable standards | Complete — see QA_Plan_V2.docx |
| Jira Sprint Board | Sprint-by-sprint task tracking, backlog, and progress evidence across all V2 development sprints | Accessible via Jira project board |
| GitHub Repository | All code, notebooks, and version history for V2 preprocessing, feature extraction, multiclass models, and Streamlit app | github.com/tshallycodes/updrs-predictor |
| Sprint Reviews | Written summaries of each sprint covering progress, blockers, and retrospective notes | Complete — see Sprint_Reviews.docx |

# 1. Executive Summary

UPDATED FOR V2  Problem reformulated from binary detection to three-class severity assessment

Version 2 of the UPDRS Predictor represents a significant clinical and methodological improvement over V1. Following supervisor feedback, the task was reformulated from binary presence/absence classification to a three-class severity assessment aligned with UPDRS clinical scoring conventions.

Rather than simply detecting whether a patient has Parkinson's Disease, V2 classifies patients into Mild, Moderate, or Severe categories — outputs that directly inform treatment planning and disease monitoring. This shift is both clinically motivated and methodologically sound: with a dataset of ~130 samples, three well-separated classes offer a better balance between clinical relevance and statistical robustness than attempting fine-grained five-class prediction.

# 2. Problem Context and Research Statement

UNCHANGED FROM V1  See PID V1 — Section: Section 2 — Background and research context

The clinical background, motivation, and dataset context remain unchanged from V1. The core problem — subjectivity of UPDRS-based clinical assessment — is the same. What changes is the research question:

## 2.2 Updated Research Statement

UPDATED FOR V2  Research question updated to reflect severity classification task

Can machine learning models trained on quantitative features extracted from finger tapping amplitude signals reliably classify Parkinson's Disease severity into clinically meaningful categories (Mild, Moderate, Severe) — providing a more actionable and reproducible alternative to UPDRS-based clinical grading?

# 3. Aims and Objectives

UPDATED FOR V2  Aim and objectives updated to reflect multiclass severity task

## 3.1 Project Aim

To develop and evaluate a multi-class machine learning classifier that assesses Parkinson's Disease severity from finger tapping amplitude signals, classifying patients as Mild, Moderate, or Severe in alignment with UPDRS scoring conventions.

## 3.2 Objectives

- Reprocess the existing dataset with improved mean-based padding replacing edge/constant padding from V1

- Apply Savitzky-Golay smoothing before feature extraction to reduce signal noise

- Re-encode UPDRS labels as three severity classes: Mild (0–1), Moderate (2–3), Severe (4)

- Extract 9 clinically grounded features per hand capturing bradykinesia, amplitude decrement, and motor variability

- Retrain SVC, SVR, Random Forest, and PyTorch MLP on the updated multiclass labels

- Model left and right hand data independently to respect Parkinson's motor asymmetry

- Evaluate all models using weighted F1-score, per-class precision/recall, and confusion matrices

- Update the Streamlit application to output severity class with confidence score and probability breakdown

# 4. Project Scope

UPDATED FOR V2  Scope updated — binary classification replaced by three-class severity prediction

## 4.1 In Scope

- Multi-class severity classification: Mild (UPDRS 0–1), Moderate (2–3), Severe (4)

- Improved preprocessing pipeline: mean-based padding and Savitzky-Golay smoothing

- 9-feature extraction pipeline with clinical justification for each feature

- Four ML models trained and evaluated independently per hand

- Updated Streamlit app with severity output and confidence scores

- Full documentation suite: PID V2, Charter V2, QA Plan V2, Sprint Reviews

## 4.2 Out of Scope — Unchanged

UNCHANGED FROM V1  See PID V1 — Section: Section 4.2 — Out of scope items remain the same as V1

# 5. Stakeholders

UNCHANGED FROM V1  See PID V1 — Section: Section 5 — Stakeholders unchanged from V1

# 6. Problem Formulation — V2 Multi-class Classification

UPDATED FOR V2  Label structure changed from binary to three severity classes

Version 2 reformulates the task as a three-class severity classification problem. UPDRS scores are consolidated into clinically meaningful groups:

| UPDRS Score | V1 Class | V2 Class | Clinical Interpretation |
| --- | --- | --- | --- |
| 0 – 1 | Healthy (0) | Mild (0) | Normal to slight impairment — minimal motor disruption |
| 2 – 3 | Split across both | Moderate (1) | Clear motor dysfunction — clinically significant impairment |
| 4 | Parkinson's (1) | Severe (2) | Significant impairment — major motor dysfunction |

Rationale for three-class structure: with ~130 samples, attempting four or five target classes would reduce model reliability and generalisation. Three classes offer a better balance between clinical relevance and statistical robustness. This grouping was recommended by the project supervisor and is methodologically sound — consolidating labels is not oversimplification but a realistic trade-off.

Known limitation: Severe cases (UPDRS 4) are underrepresented in the dataset. The model can distinguish Mild from Moderate reliably but cannot be expected to predict Severe cases until more balanced data is available. This is explicitly documented in all evaluation outputs.

# 7. Dataset

UNCHANGED FROM V1  See PID V1 — Section: Section 7 — Dataset source, size, and structure unchanged from V1

## 7.1 Changes to Data Handling in V2

UPDATED FOR V2  Padding strategy updated from edge-based to mean-based

- Amplitude signals previously padded with last observed value (edge padding) — replaced with mean-based padding in V2

- Time signals previously padded with constant 30.0 — replaced with mean-based padding in V2

- Mean-based padding is statistically neutral and preserves signal distribution, preventing artificial flat regions that distorted V1 features such as standard deviation and inter-tap intervals

- Savitzky-Golay smoothing now applied before feature extraction (window=7, polynomial order=2)

# 8. Technical Approach

## 8.1 Preprocessing

UPDATED FOR V2  Padding strategy updated — see Section 7.1

## 8.2 Feature Extraction

UNCHANGED FROM V1  See PID V1 — Section: Section 8.2 — Same 9 features extracted as in V1. See PID V1 feature table.

Features remain clinically justified and unchanged. The same 9 features are used because they directly capture the motor characteristics (bradykinesia, amplitude decrement, rhythm variability) that distinguish severity levels as well as presence/absence.

## 8.3 Models

UNCHANGED FROM V1  See PID V1 — Section: Section 8.3 — Same four models: SVC, SVR, Random Forest, PyTorch MLP

All four models are retrained on the updated multiclass labels. The training configuration is otherwise identical: 80/20 train-test split, StandardScaler, random_state=42. Models are trained separately per hand.

## 8.4 V2-Specific Evaluation

UPDATED FOR V2  Evaluation strategy updated for multiclass context

- Weighted F1-score used as primary metric (not raw accuracy) — accounts for class imbalance

- Per-class precision, recall, and F1 reported for Mild, Moderate, and Severe separately

- Confusion matrices generated for each model and each hand

- Severe class expected to show 0 support in test split — explicitly reported and discussed

- Best model identified per hand: SVC (left), Random Forest (right), both ~0.71 accuracy

# 9. Project Management

UNCHANGED FROM V1  See PID V1 — Section: Section 9 — Team, tools, and Agile approach unchanged from V1

# 10. Risk Summary

UPDATED FOR V2  Risk register updated — new V2-specific risks added

| Risk | Likelihood | Impact | Mitigation |
| --- | --- | --- | --- |
| Class imbalance — Severe cases absent from test set | High | High | Report per-class metrics; do not claim model predicts Severe; note clearly in evaluation |
| Small dataset limits deep learning performance | High | High | Treat PyTorch MLP as secondary; use SVC and RF as primary models |
| Three-class boundaries less distinct than binary | Medium | High | Use weighted F1; validate with confusion matrices; acknowledge overlap between Mild and Moderate |
| Overfitting (PyTorch MLP, 1000 epochs, small data) | Medium | High | Compare against simpler baselines; MLP accuracy ~0.57 confirms this risk materialised |
| Streamlit app failure during demo | Low | High | Test before April 6th; prepare screenshot fallback |

# 11. Constraints and Limitations

UPDATED FOR V2  Updated to reflect V2-specific constraints

- Class imbalance: Severe class (UPDRS 4) underrepresented — model cannot reliably predict this category

- No cross-validation in V2 — single 80/20 split means results depend on one partition

- No left-right hand fusion — predictions are independent per hand, missing cross-hand clinical insight

- Neural network unsuitable at this dataset size — performance confirms deep learning not advantageous here

- System is a research prototype, not clinically validated — outputs require clinical interpretation

# 12. Ethical Considerations

UNCHANGED FROM V1  See PID V1 — Section: Section 12 — Ethical considerations unchanged from V1

# 13. Success Criteria

UPDATED FOR V2  Success criteria updated — accuracy target replaced with weighted F1 threshold

| Criterion | V1 Target | V2 Target |
| --- | --- | --- |
| Classification task | Binary: Healthy vs PD | Three-class: Mild / Moderate / Severe |
| Primary metric | Accuracy | Weighted F1-score |
| Performance target | Measurable accuracy | Weighted F1 ≥ 0.65 across ≥2 models |
| Model comparison | 4 models evaluated per hand | 4 models evaluated per hand — same |
| Streamlit app | Binary prediction output | Severity class + confidence score + probability breakdown |
| Documentation | PID V1, Charter V1, QA V1 | PID V2, Charter V2, QA V2, Sprint Reviews |