## Status Report
Project Name: DSP Parkinson’s Finger Tapping Analysis
Date: January 19 2026
Summary |  |  |  | Overall Status (RAG)
Since the previous status update, the team has progressed from planning into early development. Environment setup has been completed and individual research tasks have informed the technical direction. Model development has now started, with data processing, feature engineering, and initial model construction underway. Despite temporary reduced availability due to other assessments and the holiday period, communication remained consistent and key technical milestones were achieved. The team is now fully aligned and confident moving into the testing and evaluation sprint. |  |  |  | Amber-Green (Reason: Core development has started, responsibilities are clearly assigned, and progress is aligned with the sprint plan.)
Completed Milestones and Tasks
Description | Date | Status | Owner |  | Comments
Team contract finalised and signed | Oct 14 | Completed | PM (Ebuka) |  | Roles and expectations agreed
Project charter completed & reviewed | Oct 28 | Completed | Whole team |  | Approved and aligned with client notes
Dataset obtained from client & folder structure analysed | Oct 21 | Completed | Technical team |  | Verified structure, naming, and metadata
Communication plan, QA plan, CBA, PID components completed | Nov | Completed | Whole team |  | Forms basis for PID submission
JIRA, GitHub, sprint backlog and WBS created | Nov | Completed | PM & Tech Lead |  | Supports agile workflow
Initial ML signal processing pipeline designed | Nov | Completed | Technical team |  | Includes filtering, peak extraction, feature categories
Development environment setup completed | Dec | Completed | Team |  | Enables reproducible development
AI / ML background research | Dec | Completed | Ryan |  | Informed modelling approach
Parkinson’s disease clinical research | Dec | Completed | Ebuka |  | Anchors design in UPDRS
Finger-tapping signal research | Dec | Completed | Elvis |  | Supports feature interpretation
ML signal processing pipeline design | Dec | Completed | Avyandra |  | Covers filtering, peak detection, feature flow
Signal processing research (filtering, peaks, constraints) | Dec | Completed | Avyandra |  | Justifies preprocessing decisions
ML experiments plan created | Jan | Completed | Ryan |  | Defines modelling and validation steps
Data processing & EDA | Jan | Completed | Elvis |  | Dataset profiling and quality checks
Feature engineering implementation | Jan | Completed | Avyandra |  | UPDRS-aligned interpretable features
Upcoming Milestones and Tasks
Description | Date | Status | Owner |  | Comments
Core ML model implementation | Jan | In progress | Ryan |  | Uses engineered feature set
Model evaluation and validation | Jan | Upcoming | Ebuka |  | Metrics + error analysis
Streamlit application development | Jan | Upcoming | Ebuka |  | Interactive prototype demo
Testing and evaluation sprint | Jan-Feb | Upcoming | Whole team |  | Performance, robustness, refinements
Top Risks and Issues
Issue |  | Impact | Action |  |  | Owner
Other semester deadlines and holiday period temporarily reducing team availability |  | Minor delays during early development phase; risk reduced now that full team availability has resumed | Sprint timelines adjusted, priorities rebalanced, and tasks clearly reassigned. Regular WhatsApp communication and check-ins ensured continuity and progress despite reduced availability. |  |  | PM
Misinterpreting clinical scoring criteria → invalid feature set |  | Incorrect model behaviour + rework | Use client summary + UPDRS guide + create feature checklist tied to symptoms |  |  | Research + Technical lead
Risk of using wrong signals or over-smoothing data |  | Loss of physiological detail → poor model accuracy | Enforce amplitude-only rule; SG parameters fixed; code review required |  |  | Technical team
Long sprint durations → scope creep |  | Tasks may drift; difficult to track | Mid-sprint review + tighter ticket definitions in JIRA |  |  | PM
Dataset imbalance / limited severe cases |  | Accuracy ceiling + misleading metrics | Early dataset profiling + decide on balancing strategy |  |  | Technical lead