## Status Report
Project Name: DSP Parkinson’s Finger Tapping Analysis
Date: December 2nd 2025
Summary |  |  |  | Overall Status (RAG)
The team has completed the entire project initiation phase, including the project charter, team contract, work breakdown structure, communication plan, quality assurance plan, cost–benefit analysis, early ML pipeline design, and full sprint planning. We also met with the client to clarify deliverables, dataset requirements, and clinical expectations based on MDS-UPDRS 3.4. We now fully understand the constraints: using amplitude-only signals, applying light Savitzky–Golay filtering, treating each hand as an independent case, and designing interpretable clinical features. The next sprint focuses on deepening research, validating feature design against clinical criteria, and beginning early prototype pipeline work. Overall, the project is progressing well, but workload conflict with other semester deadlines is still a notable risk. |  |  |  | Amber (Reason: Strong progress on planning, but development hasn’t started yet and workload conflicts create timing risk.)
Completed Milestones and Tasks
Description | Date | Status | Owner |  | Comments
Team contract finalised and signed | Oct 14 | Completed | PM (Ebuka) |  | Roles and expectations agreed
Project charter completed & reviewed | Oct 28 | Completed | Whole team |  | Approved and aligned with client notes
Dataset obtained from client & folder structure analysed | Oct 21 | Completed | Technical team |  | Verified structure, naming, and metadata
Communication plan, QA plan, CBA, PID components completed | Nov | Completed | Whole team |  | Forms basis for PID submission
JIRA, GitHub, sprint backlog and WBS created | Nov | Completed | PM & Tech Lead |  | Supports agile workflow
Initial ML signal processing pipeline designed | Nov | Completed | Technical team |  | Includes filtering, peak extraction, feature categories
Upcoming Milestones and Tasks
Description | Date | Status | Owner |  | Comments
Conduct detailed literature review on clinical features (bradykinesia, rhythm, hesitations, amplitude decrement) | Dec | Upcoming | Research team |  | Must align with MDS-UPDRS 3.4
Dataset exploration + preprocessing tests (light SG filtering) | Dec | Upcoming | Technical team |  | Follow client constraints strictly
Feature extraction prototype for 2–3 sample signals | Dec | Upcoming | Technical team |  | One vector per hand; 10–15 interpretable features
Sprint review & updated development plan | Dec | Upcoming | PM |  | Adjust backlog based on findings
Top Risks and Issues
Issue |  | Impact | Action |  |  | Owner
Other semester deadlines reducing team availability |  | Delays in starting development | Weekly check-ins + smaller research tasks to avoid stalling |  |  | PM
Misinterpreting clinical scoring criteria → invalid feature set |  | Incorrect model behaviour + rework | Use client summary + UPDRS guide + create feature checklist tied to symptoms |  |  | Research + Technical lead
Risk of using wrong signals or over-smoothing data |  | Loss of physiological detail → poor model accuracy | Enforce amplitude-only rule; SG parameters fixed; code review required |  |  | Technical team
Long sprint durations → scope creep |  | Tasks may drift; difficult to track | Mid-sprint review + tighter ticket definitions in JIRA |  |  | PM
Dataset imbalance / limited severe cases |  | Accuracy ceiling + misleading metrics | Early dataset profiling + decide on balancing strategy |  |  | Technical lead