## Exemplar
ROAM Analysis
| Issues | Actions | ROAM designation
Issue 1 | DSP project being deprioritised because Element 1/other semester-1 assessments feel more urgent and DSP is due later | PM structured work into longer sprints but kept this phase focused on initiation/research tasks; weekly check-ins used to keep minimal but steady progress while other deadlines peak | Mitigated
Issue 2 | Misinterpreting MDS-UPDRS 3.4 criteria and extracting features that don’t match clinical scoring (bradykinesia, rhythm, hesitations, amplitude decrement, tremor) | Team reviewed client meeting notes and MDS-UPDRS item 3.4; created a shared feature-design checklist explicitly tied to each clinical symptom to guide future feature extraction | Mitigated
Issue 3 | Using the wrong signals (velocity/frequency files) or over-smoothing amplitude so the data is no longer physiologically realistic (e.g. >10 Hz “tremor”) | Agreed pipeline standard: use amplitude-vs-time only, derive velocity from filtered amplitude if needed, constrain Savitzky–Golay parameters (small window, low polynomial order) and add a code-review checkpoint around preprocessing | Mitigated
Issue 4 | Treating left and right hands as a single combined sample, ignoring Parkinson’s asymmetry and corrupting labels | Data model updated so each hand is treated as an independent case (separate row in X with its own label); this rule is documented in the pipeline design and will be enforced in code reviews | Resolved
Issue 5 | Drifting into black-box deep learning on raw signals instead of an interpretable ML solution with 10–15 hand-crafted features as requested by the client | Defined success criteria that the first working prototype must be a feature-based, interpretable ML model; any deep learning experiments are optional and clearly secondary in the backlog | Owned
Issue 6 | Sprint scope creep due to long (≈1 month+) sprints, risking slippage and unfinished tasks | PM uses JIRA to cap sprint scope, breaks work into smaller tickets (research, design, pipeline, evaluation), and holds a mid-sprint review to re-prioritise if needed | Mitigated
Issue 7 | Reproducibility and module requirements (3 environments, FAIR report, blogs, ethics evidence, QA) being forgotten until late in the project | Created a “compliance checklist” (environments, FAIR, blogs, ethics, QA, risk log) and added related tasks into the backlog with deadlines aligned to key milestones | Owned
Issue 8 | Over-focusing on the technical ML side and under-delivering on DSP expectations (business case, stakeholders, domain context, ethics, responsible AI) | Research topics and report sections allocated explicitly (clinical domain, business case, ethics, project management); outputs feed directly into PID, quality plan and individual reports | Mitigated
Issue 9 | Loss of transparency or miscommunication with client/supervisor if individuals contact them alone | Group agreed that all emails to client/supervisor will CC the full team; key decisions and clarifications are logged in the group blog / minutes after each meeting | Resolved
Issue 10 | Dataset limitations (e.g. class imbalance, limited severe cases) may cap achievable performance and mislead expectations | Plan to profile class distribution early, apply appropriate balancing/augmentation where possible, and clearly report realistic performance bounds in the evaluation | Accepted